## Sheet1
Track Report Of OpenSource Blogging CMSD

Date	Time Spend	Issue	Work Status	Work Alloted To	Review
15th January	1day(4hour)	Design of Home page of Go Blogger cmsd	Completed	Ashwini Kumar	Accepted
17th January	1day(2hour)	Designing Css for home page	Completed	Ashwini Kumar	Accepted
25th January	1day(2 hour)	Collecting images for cmsd	Completed	Ashwini Kumar	Accepted
5th Feburary	1day(4hour)	First php file which create Database and tables	Completed	Ashwini Kumar	Working
20th Feburary	1day(2hour)	Creating Login page and its php files	Completed	Ashwini Kumar	Working
28th Feburary	1day(4hour)	Creating user site page	Completed	Ashwini Kumar	Working
1st March	1day(4hour)	Creating user blog page and its php	Mysql connectivity problem	Ashwini Kumar	Not Completed
2nd March	1day(8hour)	Connecting all files with Mysql database	Mysql connectivity problem	Ashwini Kumar	Not Completed
5th March	1day(4hour)	connecting all files with Mysql database	Completed	Ashwini Kumar	Completed
12th March	Testing(1Hour)	Got one bug(taking one content for all blogs)	solved	Ashwini Kumar	Completed